## Gantt Chart
Task | Start Date | Days to Complete
Single Socket Server Client | 2017-10-18 | 5
Main Menu Design | 2017-10-19 | 3
Server Menu Design | 2017-10-25 | 3
Pseudo Game Logic | 2017-10-19 | 4
Multi Client Connection | 2017-10-27 | 5
Multithreaded Socket Connections | 2017-10-29 | 5
Card Table Table Design | 2017-10-25 | 6
Game Logic Design | 2017-10-29 | 5
Logic with Network Implementation | 2017-11-02 | 3

## Product BackLog
User Task | User Story | Business Priority | Story Points
Single Client | As a server, I want to talk with and listen to clients | 1 | 8
Multi Client | As a server, I want to connect to multiple clients | 2 | 7
Connection Ready | As a server, I want to establish connection to allow sockets to connect | 3 | 5
Remote Connection | As a client, I want to be able to connect to server | 4 | 3
Server Menu | As a client, I want to be able to see useable menu to set up server | 5 | 4
Main Menu | As a client, I want to be able to see GUI to help me connect to server | 6 | 6
Game Entrance | As a client, I want to be able to enter the card game with my information | 7 | 5
Game Adjustment | As a client, I want to actively be able to see my opponents cards and chips | 8 | 9
Server Execution | As a server I want to actively adjust game table elements to show true state | 9 | 9
Turn Execution | As a client, I want to be able to make a turn choice | 10 | 9

## Sprint Backlog
Task Name | Responsible | Hours | Priority
Server Client Set Up | Kaiser M | 6 | 1
Game Pseudocode | Juzer Z | 3 | 2
Design Template | Andrew G | 3 | 3
Main Menu Form | Andrew G | 2 | 4
Multithreded Server | Kaiser M | 4 | 5
Server Template | Andrew G | 1 | 6
Card Table Design | Andrew G | 5 | 7
Multi Client Interaction | Kaiser M | 6 | 8
Game Code | Juzer Z | 6 | 9