## Gantt Chart
Task | Start Date | Days to Complete
Single Socket Server Client | 2017-10-18 | 5
Main Menu Design | 2017-10-19 | 3
Server Menu Design | 2017-10-25 | 3
Pseudo Game Logic | 2017-10-19 | 4
Multi Client Connection | 2017-10-27 | 5
Multithreaded Socket Connections | 2017-10-29 | 5
Card Table Table Design | 2017-10-25 | 6
Game Logic Design | 2017-10-29 | 5
Logic with Network Implementation | 2017-11-03 | 3
Game Logic Testing | 2017-11-07 | 7
Ready Up Updates Server & Client | 2017-11-08 | 3
Card Table Animation | 2017-11-11 | 7
End of Game Scoring | 2017-11-12 | 5
Sound | 2017-11-20 | 3
Unit Testing | 2017-11-23 | 4
Menu to Table Integration Testing | 2017-11-28 | 2
Due to online conversions, Ganntt chart png is also included in artifacts separately

## Product BackLog
User Task | User Story | Business Priority | Story Points
Single Client | As a server, I want to talk with and listen to clients | 1 | 8
Multi Client | As a server, I want to connect to multiple clients | 2 | 7
Connection Ready | As a server, I want to establish connection to allow sockets to connect | 3 | 5
Remote Connection | As a client, I want to be able to connect to server | 4 | 3
Server Menu | As a client, I want to be able to see useable menu to set up server | 5 | 4
Main Menu | As a client, I want to be able to see GUI to help me connect to server | 6 | 6
Game Entrance | As a client, I want to be able to enter the card game with my information | 7 | 5
Game Adjustment | As a client, I want to actively be able to see my opponents cards and chips, and know who's turn it is | 8 | 9
Server Execution | As a server I want to actively adjust game table elements to show true state | 9 | 9
Turn Execution | As a client, I want to be able to make a turn choice and have the correct execution occur | 10 | 9
Graceful Exit | As a client, I want to be able to exit the program easily without background processes | 11 | 5
Server Ready Ups | As a server, I want to now when connected clients are ready to play, and be able to relay that information to other users | 12 | 6
Player Ready Ups | As a client, I want to be able to let the server know when I am ready to play, and see when my friends are ready to play | 13 | 7
End of Game | As a client, at the end of the game, I want to be able to see my final score and see if I won | 14 | 6
Sound | As a client, I want to have a fun game environment with complimentary sound | 15 | 5
Animation | As a client, I want interactive gameplay that enhances my experience through simple card movement indicating turns being played | 16 | 6
Test Suite | As a client, I want to be able to see that all the game is working properly | 17 | 5

## Sprint Backlog
Sprint Name | Responsible | Hours | Priority
Server Client Set Up | Kaiser M | 6 | 1
Find IP and Port address to host the game on a local computer
Locally connect to the server off another instance of the game
Game Pseudocode | Juzer Z | 3 | 2
Create basis for implementation
Create UML class diagram to think about what methods are needed
Design Template | Andrew G | 3 | 3
Draw out ideas for best options for all forms that might be necessary
Talk to Kaiser about how the implementation looks on the backend to create user friendly menu
Multithreded Server | Kaiser M | 4 | 4
Figured out we need more processes, research how to create multiple threads
Run threads successfully without any deadlocks or race condition issues
Main Menu and Server Form | Andrew G | 2 | 5
Research design techniques in Visual Studio
Create the outlines for the boxes and begin to rename the variables
Make scaleable
Card Table Design | Andrew G | 5 | 6
Make cards for the table, make chips for the table
Design player spots on the boards and locate positions for all cards and chips
Multi Client Interaction | Kaiser M | 6 | 7
Using the main menu and server form, show that clients can interact with each other
Design checkboxes and messages to the console to prove the program is interacting correctly
Game Code | Juzer Z | 6 | 8
Take the Card table design and begin population of the User Interface
Assign each variable to the pieces of pseudeocoded game logic
Implement each function using proper threading to prevent freezes and race conditions
Test Game Logic | Juzer Z | 4 | 9
Upon implementation, assure each move is possible upon the respective players turns
Check edge cases like when a player runs out of chips
Make notes of timing issues with messages and responses
Create the score sheet for the end of the game
Graceful Shutdow | Kaiser and Juzer | 6 | 10
When the game comes to its completion, asssure that the user can exit out without persistant background processes.
Assure all threads are crashed when a player exits the application at any point in the game.
When one player exits the game, shut down the game for the rest of the players to indicate player gone.
When the server is shutdown, assure all the instances of the games are gracefully shutdown
Animation | Andrew | 5 | 11
Upon a player selecting the accept button, find a way to make the card slide to his deck
Create a way for the card to slide to the exact location of the next card to be populated
Show the other players the slide of a player clicking select.
Bug Sprint | All the Team | 8 | 12
Look for bugs…everywhere
Runs simulations of groups of players using different network types and variable users
Attempt gaming with more than 5
Create server running games not involved with their own computer while playing game
Run on different speeds of internet to detect latency issues
Polishing | All the Team | 5 | 13
Use differing display sizes on devices capable of playing the game
Assure animations, menus, and pop ups are working properly