## Gantt Chart
Task | Start Date | Days to Complete
Single Socket Server Client | 2017-10-18 | 5
Main Menu Design | 2017-10-19 | 3
Server Menu Design | 2017-10-25 | 3
Pseudo Game Logic | 2017-10-19 | 4
Multi Client Connection | 2017-10-27 | 5
Multithreaded Socket Connections | 2017-10-29 | 5
Card Table Table Design | 2017-10-25 | 6
Game Logic Design | 2017-10-29 | 5
Logic with Network Implementation | 2017-11-02 | 3
Full Design on png file in the folder

## Product BackLog
User Task | User Story | Business Priority | Story Points
Single Client | As a server, I want to talk with and listen to clients | 1 | 8
Multi Client | As a server, I want to connect to multiple clients | 2 | 7
Connection Ready | As a server, I want to establish connection to allow sockets to connect | 3 | 5
Remote Connection | As a client, I want to be able to connect to server | 4 | 3
Server Menu | As a client, I want to be able to see useable menu to set up server | 5 | 4
Main Menu | As a client, I want to be able to see GUI to help me connect to server | 6 | 6
Game Entrance | As a client, I want to be able to enter the card game with my information | 7 | 5
Game Adjustment | As a client, I want to actively be able to see my opponents cards and chips | 8 | 9
Server Execution | As a server I want to actively adjust game table elements to show true state | 9 | 9
Turn Execution | As a client, I want to be able to make a turn choice | 10 | 9

## Sprint Backlog
Task Name | Responsible | Hours | Priority
Server Client Set Up | Kaiser M | 6 | 1
Find IP and Port address to host the game on a local computer
Locally connect to the server off another instance of the game
Game Pseudocode | Juzer Z | 3 | 2
Create basis for implementation
Create UML class diagram to think about what methods are needed
Design Template | Andrew G | 3 | 3
Draw out ideas for best options for all forms that might be necessary
Talk to Kaiser about how the implementation looks on the backend to create user friendly menu
Multithreded Server | Kaiser M | 4 | 4
Figured out we need more processes, research how to create multiple threads
Run threads successfully without any deadlocks or race condition issues
Main Menu and Server Form | Andrew G | 2 | 5
Research design techniques in Visual Studio
Create the outlines for the boxes and begin to rename the variables
Make scaleable
Card Table Design | Andrew G | 5 | 6
Make cards for the table, make chips for the table
Design player spots on the boards and locate positions for all cards and chips
Multi Client Interaction | Kaiser M | 6 | 7
Using the main menu and server form, show that clients can interact with each other
Design checkboxes and messages to the console to prove the program is interacting correctly
Game Code | Juzer Z | 6 | 8
Take the Card table design and begin population of the User Interface